## KYC Fin Crime Automation
Project 1. Google Agentic AI - KYC
Start Date for YearX is 01/09/25
Workstream Lead:
Management Lead:
|  |  | Developers | Project Team Members
1 | Client Onboarding AI Agent |  | N/A | X
2 |  |  |  | X
3
4
1.1 Client Onboarding AI Agent
ID | Deliverable Name | Deliverable Description (2 lines) | Project Description | Project Delivery Owner | Deliverable Due Date | Deliverable Document Name | Technological Uncertainties
1.1.1 | Policy Interpretation Agent | Create and train an AI agent which can digest policy as code and produce a list of KYC requirements based on entity type, jurisdiction, risk rating etc. | The company is focused on advancing agentic AI capabilities to drive automation across the KYC lifecycle. This PoC is being developed to showcase the tangible potential of agentic systems in streamlining and enhancing KYC processes. It will serve as a strategic accelerator, demonstrating the value we can deliver and reinforcing our broader services offering in this rapidly evolving space. |  | 2025-07-01 |  | None at this time
1.1.2 | Data & Document Collection Agent | Create and train an AI agent which is capable of extracting company data from 3rd party sources, cleansing, and validating that data and the transferring it to a KYC onboarding tool for storage. |  |  | 2025-07-01 |  | None at this time
1.1.3 | Screening Agent | Create and train an AI agent which pulls data from a 3rd party screening provider such as Worldcheck and conducts reviews of the data to discount false positive, flag genuine matches and makes recommendations for next steps. |  |  | 2025-07-01 |  | None at this time
1.1.4 | Risk Assessment Agent | Create and train an AI agent which can make a determination of a customers overall risk based on the data points and risk factors captured by the previous screening and data collection agents. |  |  | 2025-07-01 |  | None at this time
1.1.5 | Profile Completion Agent | Train an AI agent to product an overall PDF/word KYC report of all of the data collected and findings throughout the case. |  |  | 2025-07-01 |  | None at this time
1.1.6 | Agent Interface | Create an interface which can be used to demonstrate the agentic workflow, flag case for human review and input/store collected customer KYC data. Intention at present to use SalesForce. |  |  | 2025-07-01 |  | None at this time
1.1.7
1.2 Intelligent Document Processing & Customer Outreach Tool
ID | Deliverable Name | Deliverable Description (2 lines) | Project Description | Project Delivery Owner | Deliverable Due Date | Deliverable Document Name | Technological Uncertainties
1.2.1 | Workflow Mapping | Mapping the end to end workflow of the solution in miro | Working with EPAM developers to create an intelligent document processing tool and automated customer outreach solution which is capable of processing documents, validating completness and accuracy, extracting and validating the data. The customer outreach tool is an automated solution that handles automated emails, chasers to non-responders and communicates any errors to the customer. |  | 2025-03-25 |  | None at this time
1.2.2 | Customer Outreach UI in Flowable | Creating a user interface for the solution |  |  | 2025-04-25 |  | None at this time
1.2.3 | Intelligent Document Processing in DEPS | Creating intelligent document processing capability via DEPs |  |  | 2025-04-30 |  | None at this time
1.2.4 | MI Dashboard | Producing a power-bi dashboard to sit over the top of the solution |  |  | 2025-06-30 |  | None at this time
1.2.5 | ID&V KYC Solution | [5 empty] | None at this time
1.3 Project Name
ID | Deliverable Name | Deliverable Description (2 lines) | Project Description | Project Delivery Owner | Deliverable Due Date | Deliverable Document Name | Technological Uncertainties
1.3.1
1.3.2
1.3.3
1.3.4
1.4 Project Name
ID | Deliverable Name | Deliverable Description (2 lines) | Project Description | Project Delivery Owner | Deliverable Due Date | Deliverable Document Name | Technological Uncertainties
1.4.1
1.4.2
1.4.3
1.4.4

## Gantt Chart
ID | Project | Deliverable | Target Start Date | Target End Date | Status | % Complete | Owner | Y1 Month 1 | Y1 Month 2 | Y1 Month 3 | Y1 Month 4 | Y1 Month 5 | Y1 Month 6 | Y1 Month 7 | Y1 Month 8 | Y1 Month 9 | Y1 Month 10 | Y1 Month 11 | Y1 Month 12
1.1.1 | Client Onboarding AI Agent | Policy Interpretation Agent | 2025-06-01 | 2025-07-01 | In Progress
1.1.2 | Client Onboarding AI Agent | Data & Document Collection Agent | 2025-06-01 | 2025-07-01 | In Progress
1.1.3 | Client Onboarding AI Agent | Screening Agent | 2025-06-01 | 2025-07-01 | In Progress
1.1.4 | Client Onboarding AI Agent | Risk Assessment Agent | 2025-06-01 | 2025-07-01 | In Progress
1.1.5 | Client Onboarding AI Agent | Profile Completion Agent | 2025-06-01 | 2025-07-01 | In Progress
1.1.6
1.1.7
1.2.1
1.2.2
1.2.3
1.2.4
1.2.5
1.3.1
1.3.2
1.3.3
1.3.4
1.4.1
1.4.2
1.4.3
1.4.4

## Individual Timesheet - Person 1
Year | 2025
Month(s) | March, April, May & June
Office Location e.g. Newry | Newry |  | added by FD
Payroll Location e.g. UK | UK |  | added by FD
Employee ID |  |  | added by FD
Employee Name
Supervisor Name
Job Role | Principal Consultant
Project Code
Day of Week | DATE | Project/Training hours | Activity Undertaken (link to Deliverable name & no.)
Mon | 2025-03-03 | 4 | User stories & business requirements for customer outreach (1.2.2, Customer Outreach UI in Flowable)
Tue | 2025-04-03 | 4 | User stories & business requirements for customer outreach (1.2.2, Customer Outreach UI in Flowable)
Tue | 2025-11-03 | 5 | User stories & business requirements for document processing (ISDA form) (1.2.3, Intelligent Document Processing in DEPS)
Wed | 2025-12-03 | 3 | User stories & business requirements for document processing (KYC form) (1.2.3, Intelligent Document Processing in DEPS)
Fri | 14/3/2025 | 3.5 | MIRO workflow map of end to end process (1.2.1, Workflow Mapping)
Tue | 2025-01-04 | 2 | Drafting customer outreach templates (1.2.2, Customer Outreach UI in Flowable)
Tue | 2025-08-04 | 2 | Drafting v2 outreach templates (1.2.2, Customer Outreach UI in Flowable)
Tue | 29/5/2025 | 3 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
Wed | 30/5/2025 | 2 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
Thu | 25/4/25 | 2 | Solution Demo (All deliverables under project 1.1)
Fri | 2025-05-30 | 4 | Creating policy for policy interpretation agent to digest. (1.1.1, Policy Interpretation Agent)
Tue | 2025-06-03 | 4 | Writing business requirements & user stories for all agents (All deliverables under project 1.1)
Wed | 2025-06-04 | 4 | Writing business requirements user stories for all agents (All deliverables under project 1.1)
Thu | 2025-06-05 | 4 | Mapping data points and where they can be collected. (1.1.2, Data Collection Agent)
Fri | 2025-06-06 | 5 | Building Risk Assessment Matrix. (1.1.4, Risk Assessment Agent)
Mon | 2025-06-09 | 2 | Locating and assessing public screening data. (1.1.3, Screening Agent)
Tue | 2025-06-10 | 3 | Drafting an output template for the final KYC report. (1.1.5, Profile Completion Agent)
Fri | 20/6/2025 | 2 | Prep for agentic demo (All deliverables under project 1.1)
Mon | 23/6/2025 | 2 | Demo of all agents (All deliverables under project 1.1)
Total hours |  | 30
Employee Signed |  | Supervisor/Manager Signed
Date |  | Date

## Individual Timesheet - Person 2
Year | 2025
Month(s) | March, April, May & June
Office Location e.g. Newry | Newry |  | added by FD
Payroll Location e.g. UK | UK |  | added by FD
Employee ID |  |  | added by FD
Employee Name
Supervisor Name
Job Role | Principal Consultant
Project Code
Day of Week | DATE | Project/Training hours | Activity Undertaken (link to Deliverable name & no.)
Friday | 2025-06-13 | 3 | Discussion and Working on creating user stories for all agents for demo (Applies to all of the deliverables under project 1.1)
2025-06-17 | 2025-06-24 | 2 | Working on creating user stories for all agents for demo (Applies to all of the deliverables under project 1.1)
2025-06-19 | 2025-06-19 | 2 | Working on creating user stories for all agents for demo (Applies to all of the deliverables under project 1.1)
2025-06-20 | 2025-06-20 | 2 | Working on creating user stories for all agents for demo (Applies to all of the deliverables under project 1.1)
Monday | 2025-06-23 | 2 | Filming Agentic Demo Applies to all deliverables under project 1.1
2025-06-25 | 2025-06-25 | 4 | Working on creating user stories for all agents for demo (Applies to all of the deliverables under project 1.1)
Thursday | 2025-06-26 | 2 | Building out draft Dashboard for Agentic Demo - Applies to all deliverables under project 1.1
Total hours |  | 17
Employee Signed |  | Supervisor/Manager Signed
Date |  | Date

## Individual Timesheet - Person 3
Year | 2025
Month(s) | March, April, May & June
Office Location e.g. Newry | Newry |  | added by FD
Payroll Location e.g. UK | UK |  | added by FD
Employee ID |  |  | added by FD
Employee Name
Supervisor Name
Job Role | Principal Consultant
Project Code
Day of Week | DATE | Project/Training hours | Activity Undertaken (link to Deliverable name & no.)
2025-05-15 | 2025-05-15 | 4 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
2025-05-16 | 2025-05-16 | 5 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
2025-05-19 | 2025-05-19 | 4 | Business requirements and user stories for KYC ID&V Solution (1.2.4, KYC ID&V Solution)
2025-05-20 | 2025-05-20 | 4 | Business requirements and user stories for KYC ID&V Solution (1.2.4, KYC ID&V Solution)
Wed | 2025-05-21 | 5 | Business requirements and user stories for KYC ID&V Solution (1.2.5, KYC ID&V Solution)
Mon | 2025-06-02 | 2 | Writing business requirements & user stories for all agents (All deliverables under project 1.1)
Tue | 2025-06-03 | 4 | Writing business requirements & user stories for all agents (All deliverables under project 1.1)
2025-06-03 | 2025-06-03 | 3 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
Wed | 2025-06-04 | 2 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
Wed | 2025-06-11 | 3 | Business requirements and user stories for KYC MI Dashboard (1.2.4, MI Dashboard)
Total hours |  | 36
Employee Signed |  | Supervisor/Manager Signed
Date |  | Date